## International Development Week
Communications Plan: International Development Week 2020
Theme: #Goforthegoals
Date/Time Frame | What | Goal | Responsibility | Status | Webpage | BLOG | Newsletter | Social Media | Email to list | YouTube | WHO | NOTES
Before Dec 20 | SDG the church wants to highlight to help animate global partner stories selected : See https://sustainabledevelopment.un.org/sdgs | Use a different goal each day to highlight UCC story | Pat/Thivan | Done
Week of Jan 20 | Blog about what sustainable development // or news announcement linking to resources | Introduce / share with UCC audience why sustainable development is important | Pat/Thivan (Aimee to edit) | In Development |  | Yes - write up on What is SDG, link to video from UN | E-ssentials - January 28 | Yes | E-ssentials - January 28
International Development Week Feb 2-8 Publishing, Promo Existing Content, and Social Media Plan
Feb 2 | Kick-off | Re-promo Thivan/Pat blog |  | In Development |  | Yes |  | Yes
Feb 3 | Goal 1 - ECLOF (Ecuador and Philippines) Microfinance | Post links to new stories, Post existing Minute for Mission videos. Other possible content ideas for posts 1)Picture Essay- style blog 2) Live stream/video of Thivan/Ayldia Foods Security event onf UAJ Facebook 3) Pictures from partners with a short caption to describe partnership/work and how it relates to the goal. Include a blurb on how people can contribute to the SDGs in their communities | Aimee (write) | In Development |  |  |  | Yes
Feb 4 | Goal 2 and 5 - NCCK and OAIC (Kenya) Small holder farms |  | Aimee (write) | In Development |  | Yes--Lift up smallholder farms |  | Yes |  | Minutes for Mission - OAIC
Feb 5 | Goal 3 - NECC (Palestine) - Well Baby Clinic / KAACR (Kenya) - Child Rights |  | Promote 2019 M4M video | In Development |  |  |  | Yes |  | Minutes for Mission
Feb 6 | Goal 4 - Women for Change (Zambia) - Keep Girls in School, CEPALC (Colombia), Human Rights and Advocacy Research Foundation (India) Equip a Child for School |  | Aimee (write) | In Development |  | Yes - use resource from GWV (Pat provided) |  | Yes
Feb 7 | Goal 13 - COP25 (UCC) |  | Promote video content from Nov 2019 | In Development |  |  |  | Yes |  |  |  | Jennifer to provide resources
Feb 8 | Goal 2 - UCC - Food for the North |  | Promote Gifts with Vision gift | In Development |  |  |  | Yes |  |  |  | Thivan to talk to Dallas in NIC for resources.
Cross Promo / More Communications
Jan 28 | Essentials Newsletter | Promo International Development week/ OR repromo Pat/Thivan Blog | Aaron
Feb 3 | UAJ Newsletter | Promo International Development week/ or other relevent content related to the day's goal | Jennifer
Week of Feb 2 | Gifts with Vision special email via mailchimp | Highlight how donors gifts have helped | Jennifer/ Ruth

## Sheet2
Sustainable Development Goal | Partner | Project | Country | Story / picture readily available? | Minutes for Mission
SDG 1 – No Poverty | ECLOF | Microfinance |  | Email Nicholas at ECLOF
SDG 1 and 2 – No Poverty, Zero Hunger | OAIC | Chicken Farming | Kenya | ​Lift up importance of small hold farms for feeding families (info in gordon butler report). Info & pic from 2014 in IDW Onedrive folder. | https://www.youtube.com/watch?v=WyiCXSXrtBA&list=PLQDu-SgFb3RhYlxVfQOxbo1DjO9ezW-sR&index=12&t=0s
SDG 2 and 5 – Zero hunger, Gender Equality | National Council of Churches of Kenya or OAIC | Conservation Agriculture | Kenya | Yes – Thivan and Wendy’s trip
SDG 2 | UCC, Indigenous Ministries | Food for the North | Canada | Gifts with Vision
SDG 2 | UCC | Eight Hot Meals | Canada | Gifts with Vision
SDG 3 – Good health and well-being | Near East Council of Churches | Well Baby Project | Palestine | Yes – Minutes for Mission
SDG 4, Quality Education | Women for Change | Keep Girls in School | Zambia | Yes – Gifts with Vision, Minutes for Mission, ​UCW Updates in Onedrive IDW folder
SDG 5, Gender Equality | Astha Sansthan | Single Women’s empowerment | India | Yes – CFLI and Japhet
SDG 13, Climate Action | UCC | COP25 | Spain | Jennifer has the story
SDG 16 – Peace, Justice and Strong Institutions for all | UCC | Equine Program | Canada | Yes – Minutes for Mission. Need to talk to I
SDG 6 - Clean water and sanitation | People’s Action Forum in Zambia | Borehole | Zambia | ​In Ondrive - IDW folder
SDG 4, 16 | CEPALC | Education Program | Colombia | Gifts with Vision